Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Storypoints)

| Date | 15 February 2026 |
| --- | --- |
| Team ID | LTVIP2026TMIDS78982 |
| Project Name | FlightFinder – Navigating Your Air Travel Options |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | As a user, I can register using email and password. | 2 | High | Frontend Dev |
| Sprint-1 |  | USN-2 | As a user, I receive confirmation email after registration. | 1 | High | Backend Dev |
| Sprint-2 |  | USN-3 | As a user, I can register using Facebook login. | 2 | Low | Backend Dev |
| Sprint-1 |  | USN-4 | As a user, I can register using Gmail login. | 2 | Medium | Backend Dev |
| Sprint-1 | Login | USN-5 | As a user, I can log into the application by entering email & password | 1 | High | Backend Dev |
| Sprint-1 | Dashboard | USN-6 | As a user, I can view my dashboard after login. | 2 | High | Frontend Dev |
| Sprint-1 | Flight Search | USN-7 | As a user, I can search flights by source, destination, and date. | 3 | High | Backend Dev |
| Sprint-2 | Flight Search | USN-8 | As a user, I can filter flights by price and airline. | 2 | Medium | Frontend Dev |
| Sprint-2 | Flight Booking | USN-9 | As a user, I can select a flight and enter passenger details. | 3 | High | Full Stack Dev |
| Sprint-2 | Payment | USN-10 | As a user, I can make secure online payment. | 5 | High | Backend Dev |
| Sprint-2 | Booking Management | USN-11 | As a user, I can receive booking confirmation and e-ticket. | 3 | High | Backend Dev |
| Sprint-2 | Booking Management | USN-12 | As a user, I can view my booking history. | 2 | Medium | Frontend Dev |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 01 Feb 2026 | 06 Feb 2026 | 20 | 06 Feb 2026 |
| Sprint-2 | 20 | 6 Days | 08 Feb 2026 | 13 Feb 2026 | 18 | 14 Feb 2026 |
| Sprint-3 | 20 | 6 Days | 15 Feb 2026 | 20 Feb 2026 | 20 | 20 Feb 2026 |
| Sprint-4 | 20 | 6 Days | 22 Feb 2026 | 27 Feb 2026 | 19 | 28 Feb 2026 |

# Velocity Calculation

Total Story Points Completed:

Sprint-1 = 20
Sprint-2 = 18
Sprint-3 = 20
Sprint-4 = 19

Total Completed = 20 + 18 + 20 + 19 = 77

Number of Sprints = 4

### Velocity = 77 / 4

### Velocity = 19.25 ≈ 19 Story Points per Sprint

Team Velocity = 19 Story Points per Sprint

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

A Burndown Chart shows:

- X-axis → Sprint Days

- Y-axis → Remaining Story Points

### Example for Sprint-1 (20 Story Points, 6 Days)

| Day | Remaining Story Points |
| --- | --- |
| Day 1 | 20 |
| Day 2 | 17 |
| Day 3 | 14 |
| Day 4 | 10 |
| Day 5 | 5 |
| Day 6 | 0 |

This shows steady progress until all tasks are completed by Day 6.

# Final Summary

- Total Planned Story Points = 80

- Total Completed Story Points = 77

- Average Velocity = 19 Story Points per Sprint

- Minor spillover occurred in Sprint-2 and Sprint-4

- Overall project delivered successfully within planned timeline